## Sheet1
ID | Sprint | Theme | Role | Task | Reason | LOE | Time spent | Time Left | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | Note
1.1 | 1 | Planning | As a software engineer, I want to know what I am programming | Planning | Starting project | 1 | 5 | 0 | 1 | 1 | 1 | 1 | 1 | [13 empty] | Gathering requirements from the customer
2 | 1 |  |  | Writing System Requirements Specification | Need documentation | 2 | 2 | 1 |  |  | 1
3 | 2 |  |  | Writing System Design Document | Need documentation | 3 | 3 | 2 |  |  |  | 1
4 | 2 |  |  | Designing Project Stucture | Complete design | 2 | 2 | 0 |  |  |  |  | 2 | [13 empty] | What classes and platforms we will use
5 | 2 |  |  | Designing UI | Complete design | 1 | 1 | 0 | [5 empty] | 1 | [12 empty] | Plan out how the interface will look
6 | 3 | Implementation | As a user, I want to log in to save a trip | Implementation of logging in | Coding | 2 | 3 | 0 | [6 empty] | 1 | 1 | 1
7 | 3 |  | As an admin, I want to change locations | Implementation of admin privilages | Coding | 3 | 7 | 0 | [7 empty] | 1 | 4 | 2
8 | 3 |  | As a user, I want to find the easiest way to travel to all the selected locations | Implementation of algorithm | Coding | 5 | 6 | 0 | [9 empty] | 2 | 2 | 2
9 | 3 |  | As a user, I want to receive emails to schedule a trip | Implementation Calendar | Coding | 4 | 4 | 1 | [10 empty] | 2 | 1
10 | 4 | Testing | As a developer, I want to ensure the system runs smoothly | Testing- create a user/login | Testing to make sure it works | 5 | 5 | 0 | [11 empty] | 4 | 1 | [5 empty] | Can the regular users and admins login and can users create new accounts.
11 | 4 |  |  | Testing- Modify Locations | Testing to make sure it works | 4 | 4 | 2 | [12 empty] | 1 | 1 |  |  |  |  | Make sure admin can add, delete, and change locations
12 | 4 |  |  | Testing- Shortest distance Algorithm | Testing to make sure it works | 6 | 6 | 0 | [13 empty] | 3 | 3 |  |  |  | Does the algorithm calculate correctly
13 | 4 |  |  | Testing- get email updates | Testing to make sure it works | 4 | 3 | 1 | [14 empty] | 2 | 1 |  |  | Send email to user to schedule a trip
14 | 4 |  | As a developer, I want to ensure everything works together | Testing- Integration of System | Testing to make sure it works | 10 | 10 | 0 | [13 empty] | 2 | 1 | 4 | 3 |  | Make sure all components work together
15 | 5 | Documentation | As a developer, I want to deliver updated documents | Update documents | Need documentation | [7 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1
16 | 5 | Documentation | As a user, I want to be able to read a help document about the system | Admin/User docs | Need documentation | 8 | 8 | 2 | [13 empty] | 1 |  |  | 2 | 3 | Writing help documentation
17 | 5 | Demo | As a customer, I want to ensure the product works | Demo | Final Presentation | 2 | 2 | 1 | [17 empty] | 1 | Demonstrate project to the customer and class
18 | [6 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
19 | [6 empty] | 0 | 0
|  |  |  | TOTAL |  | 62 | 71 | 10 | 1 | 1 | 2 | 2 | 4 | 1 | 1 | 2 | 5 | 5 | 4 | 7 | 2 | 7 | 6 | 5 | 6 | 4
|  |  |  | Daily burnout |  | -17 |  |  | 5 | 4 | 5 | 4 | 5 | 4 | 5 | 4 | 5 | 4 | 4 | 5 | 4 | 4 | 4 | 5 | 4 | 4
|  |  |  | Total time left (from estimate) |  |  | Estimate | 62 | 57 | 53 | 48 | 44 | 39 | 35 | 30 | 26 | 21 | 17 | 13 | 8 | 4 | 0 | -4 | -9 | -13 | -17
|  |  |  | Total time left (from spent) |  |  | Burnout | 71 | 70 | 69 | 67 | 65 | 61 | 60 | 59 | 57 | 52 | 47 | 43 | 36 | 34 | 27 | 21 | 16 | 10 | 6